## 2020.6.30
Decentralized Capital Budget Programme - 2019 - PUTTALAM District | [24 empty] | Annexure No.1
Physical and Financial Progress of the 2019
Divisional Secretariat Division (a) |  |  | Name: MADAMPE
1187
SN |  | Name of MP | Name of Project | අංශය | G.N. Division (b) |  | Sector |  | Type of Project (Construction/Goods&Services) | Total Estimate Cost (Rs.) |  | Allocation (Rs.) | Expenditure (Rs.) | Unit of Measure | Physical Progress (c) | [9 empty] | No of Beneficiaries | Remarks BILLS
[5 empty] | Name | No |  |  |  | With VAT | Without VAT |  |  |  | A | B |  |  |  | C | D | E | F | G
[16 empty] | B1 | B2 | B3 | B4
1 | 1 | Hon.M.P Sanath Nishantha | Completting balance work of comeunity trainning hall at Galahitiyawa | Manakkulama | 534 C Galahitiyawa | 10563 | CD | c | Construction |  | 266529.19 | 275000 | 266529.19 | [10 empty] | 1 | 100
2 | 2 |  | Supplying plastic chairs for PRAJAMULA society at Galmuruwa North |  | 544 Galmuruwa North | 10575 | CD | cb | Goods |  | 29388 | 30000 | 29388 | 31plastic chairs without arm | [9 empty] | 1 | 200
3 | 3 |  | Building a Room for Sewapiyasa at manakkulama Sewapiyasa |  | 556 B Manakkulama | 10539 | CD | s | Construction |  | 63762.58 | 46000 | 44115.57 | [10 empty] | 1 | 1340 | 44115.57
4 | 4 |  | Supplying a hut for Rural Develament society at Rathmalagara |  | 545 A Rathmallagara |  | CD | cb | Goods |  | 35000 | 35000 | 35000 | 15*20 hut 01 | [9 empty] | 1 |  | 35000
5 | 5 |  | Restoreting the fence infront of the public cemetry at Mahaga South |  | 547 Mahagama south |  | CD | OTHER | Construction |  | 147109.33 | 150000 | 145500 | [10 empty] | 1 | 650 | 145500
6 | 6 |  | Supplying cooking wears and buffe set for Isuru subasadaka society at mahagama south |  | 547 Mahagama south | 10536 | CD | cb | Goods |  | 50750 | 50000 | 50000 | 20kg/8kg/3kg cooking wears and 10L/7L/5L buffet set | [9 empty] | 1 | 100
7 | 1 | Hon.M.P. Ashoka Priyantha | Givings equipments for socities and pre schools |  | Divisional Secretariat | 1187 | CD | cb | Goods |  | 88546 | 90000 | 88546 | 30 plastic chairs and 01 hut/ damro chairs 21 | [9 empty] | 1 | 1898 | 88546
8 | 2 |  | Supplying chairs for Eksath mithuru kalla welfaire society |  | 554 A Harindragama | 10538 | CD | cb | Goods |  | 14550 | 15000 | 14550 | 15 chairs with arm | [9 empty] | 1 | 15
9 | 3 |  | Supplying desks and chairs for sri Bodimalu viharaya |  | 545 Nankadawara | 10548 | CD | e | Goods |  | 19448 | 20000 | 19448 | 34 small chairs | [9 empty] | 1 | 300
10 | 4 |  | Supplying a steel Cupboard for funarulaid society at Pukulama |  | 540 A Pukulama |  | CD | cb | Goods |  | 12750 | 15000 | 12750 | 01piyestar Cupboard | [9 empty] | 1 | 980
11 | 5 |  | Complete the balance work Pothukolawaththa comiunity hall at Galmuruwa South |  | 542 A Galmuruwa South |  | CD | c | Construction |  | 196620.75 | 200000 | 194000 | [10 empty] | 1 | 154 | 194000
12 | 6 |  | Supplying elecrocity for the comeunity hall of Victoriya Elegance society |  | 534 C Galahitiyawa | 10563 | EL | El | Goods |  | 19 765.16 | 20000 | 19765.16 | connection | [9 empty] | 1 | 100
13 | 7 | Hon.M.P. Ashoka Priyantha | Supplying chairs for Ekamuthu funarulaid society |  | 534 A Pothuwila |  | CD | cb | Goods |  | 14985 | 15000 | 14985 | 15 damro armless chairs | [9 empty] | 1 | 313
14 | 8 |  | Supplying chairs for Ekamuthu KANTHA society |  | 540 Thaniwellegama |  | CD | cb | Goods |  | 14670 | 15000 | 14670 | 15 chairs with arm | [9 empty] | 1 | 50
15 | 9 |  | Supplying cooking wears for Ekamuthu funarulaid society at Uraliyagara |  | 533 A Mallawagara |  | CD | cb | Goods |  | 19100 | 20000 | 19100 | 7 pots / 1 screper machine | [9 empty] | 1 | 157
16 | 10 |  | Supplying a hut for Suhada Kantha Samithiya |  | 547 A Mahagama North | 10535 | CD | cb | Goods |  | 42000 | 40000 | 40000 | 10*12 hut 01 | [9 empty] | 1 | 120
17 | 11 |  | Supplying equipment for registered societies |  | Divisional Secretariat |  | CD | cb | Goods |  | 34230 | 35000 | 34230 | 35 plastic chairs | [9 empty] | 1 |  | 34230
18 | 12 |  | Supplying Plastic tables for VIDATHA SAMPATH CENTER at Uraliyagaraya |  | 533 Uraliyagara | 10571 | CD | cb | Goods |  | 15000 | 15000 | 15000 | 4 plastic tables | [9 empty] | 1 |  | 15000
19 | 13 |  | Supplying uniform for the players at Nankadawara Sport Club |  | 545 Nankadawara | 10548 | CD | SPO | Goods |  | 17500 | 18000 | 17500 | 21 T - shirts | [9 empty] | 1 |  | 17500
20 | 14 |  | Supplying chairs for Anthoni Munidunge church at Athuwna |  | 547C Athuwana | 10534 | CD | R | Goods |  | 19908 | 20000 | 19908 | 21plastic chairs with arm | [9 empty] | 1 |  | 19908
21 | 15 |  | Supplying chairs for Vasana Rural development society |  | 560 A Pambala south |  | CD | cb | Goods |  | 19560 | 20000 | 19560 | 20 plastic chairs | [9 empty] | 1 |  | 19560
22 | 1 | Hon.M.P.Niroshan Perera | Supplying a 15*10 hut and plastic chairs for JAMIUL ALPHARIYA JUMMA church |  | 537 Marakkalagama |  | CD | cb | Goods |  | 64532 | 65000 | 64532 | 15*10 hut 01/9 plastic chairs | [9 empty] | 1 |  | 64532
23 | 1 | Hon.M.P. Priyankara Jayarathna | Building a Foundation for RATHNAGIRIYA Eksath funarulaid hall |  | 545 B Rathnagiriya |  | CD | C | Construction |  | 198057.23 | 200000 | 175692.21 | [10 empty] | 1 | 105 | 175692.21
24 | 2 |  | Building funarulaid society hall at Mahagama north |  | 547 A Mahagama North | 10535 | CD | C | Construction |  | 267835.47 | 200000 | 194000 | [10 empty] | 1 | 387 | 194000
25 | 3 |  | Supplying a buffe set for Ekamuthu funarulaid society at Egodayagama |  | 535 A Egodayagama |  | CD | cb | Goods |  | 49800 | 50000 | 49800 | buffe set 10L - 2/ 07L-1/5L-1/3L- 1/ Plats 22/glass set 03/spoons 20 | [9 empty] | 1 | 501
26 | 4 |  | Supplying a buffe set for suduaraliya women society at Irattakulama north |  | 534 Irattakulama north | 10556 | CD | cb | Goods |  | 50000 | 50000 | 50000 | buffe set 3L - 4/ 7L- 02/ 10L -01/Plastic cups 200/ 01 jug / 100l bucket 01/ 01 basin 30L / Spoons 3/ pot 01 | [9 empty] | 1 | 250
27 | 5 |  | Supplying cooking wears for srikatha women society at Irattakulama south |  | 534 B Irattakulama south |  | CD | cb | Goods |  | 49004 | 50000 | 49004 | pots 10kg -1/7kg-1/ 5kg-3/ gass cooker 01/ gass cillinder 01 | [9 empty] | 1 | 80
28 | 6 |  | Supplying plastic chairs for Samadi dahampasala |  | Idigaswila |  | CD | e | Goods |  | 99900 | 100000 | 99900 | Damro plastic armless chairs 100 | [9 empty] | 1 | 75
29 | 1 | Hon.M.P Rangebandara | Developing Horagahahena 1 st lane at Diyabubula road with gravel |  | 557 Tabagalla |  | RA | rog | Construction |  | 97184 | 100000 | 97000 | [10 empty] | 1 | 30 | 97000
30 | 2 |  | Supplying chairs and a hut for Grasland Dummalasuriya funarulaid society |  | 542 A Galmuruwa South |  | CD | cb | Goods |  | 49470 | 50000 | 49470 | 51 chairs with arm | [9 empty] | 1 | 75
31 | 3 |  | Supplying chairs and a VIP hut for Rural development society |  | 541 Mugunuwatawana | 10578 | CD | cb | Goods |  | 49470 | 50000 | 49470 | 51 chairs without arm | [9 empty] | 1 | 350
32 | 4 |  | Supplying cooking wears for Eksath funarulaid society at Dankale Galmuruwa |  | 543 Kudirippuwa | 10560 | CD | cb | Goods |  | 34800 | 35000 | 34800 | pots 10kg-1/7kg- 3/ 15kg - 1/silver basins 02 /plates 50/plastic bucket 5 | [9 empty] | 1 | 300
33 | 5 |  | Supplying water pumpe for Galmuruwa Uthura Govisanwidanaya |  | 544 Galmuruwa North | 10575 | CD | a | Goods |  | 85215 | 60000 | 60000 | 3'' water pump 01 | [9 empty] | 1 | 30
34 | 6 |  | Supplying a VIP hut for Ekamuthu elders society (HSE/2012/601236115/NWP) at |  | 551 Uraliya | 10556 | CD | cb | Goods |  | 42000 | 40000 | 40000 | 10*12 hut 01 | [9 empty] | 1 | 268
35 | 7 |  | Supplying a VIP hut for Samagitharu Sports club (වප/පුත්/මාද/ක්‍රී.ස.17) at Uraliya |  | 551 Uraliya | 10556 | CD | cb | Goods |  | 42000 | 40000 | 40000 | 10*12 hut 01 | [9 empty] | 1 | 238 | 40000
36 | 8 |  | Supplying a VIP hut for funarulaid society (ලි.ප.අංක 2008/8) at Nelumpokuna |  | 540 Nelumpokunna | 10580 | CD | cb | Goods |  | 42000 | 40000 | 40000 | 10*12 hut 01 | [9 empty] | 1 | 150
37 | 9 |  | Supplying a Arch shape VIP hut for funarulaid society at Sembukattiya |  | 553 Sembukattiya | 10555 | CD | cb | Goods |  | 40000 | 40000 | 40000 | Arch shape hut 01 | [9 empty] | 1 |  | 40000
38 | 10 |  | Supplying plastic chairs for SANTHA SEBASTHIAN church at pambala north |  | 560 Pambala North | 10552 | CD | R | Goods |  | 39770 | 40000 | 39770 | 41plastic chairs with arm | [9 empty] | 1 | 260
39 | 11 |  | Supplying a computer for Mahagama kanitu viduhala |  | 547 Mahagama south | 10536 | CD | e | Goods |  | 79900 | 75000 | 75000 | 01 computer / 01 pinter | [9 empty] | 1 | 139 | 75000
40 | 12 |  | Laying gravel for 1st lane at ponnankanniya ( near the temple ) |  | 555 Ponnankanniya |  | r | rog | Construction |  | 194368 | 200000 | 194000 | [10 empty] | 1 | 6 | 194000
41 | 13 |  | Developing Pahalagama Road ( Near the home of mrs . janaka's ) |  | 555 Ponnankanniya |  | r | tar | Construction |  | 192881.2 | 200000 | 192881.2 | 64m | [9 empty] | 1 |  | 192881.2
42 | 1 | Hon.M.P Santha Sisira kumara | Supplying eqvipments for senanayaka vidyalaya at athuwana |  | 547C Athuwana | 10534 | CD | e | Goods |  | 201100 | 200000 | 200000 | Ahuja microphone 01/Ahuja colom speker 02 /Ahuja SSB 80 w amp 01/ 5 core Mic Stand 01/12 '˝ maxtone simble 02 / /12 '˝ maxtone side drum 01/ 48'˝ nicale shaft 01/ melodica 04/ 06 '˝ traingle 04 / 08 '˝ pntharu 4/double see saw 01/ pyramid ladder 01 / mat slider 01 | [9 empty] | 1 | 123 | 200000
43 | 2 |  | Supplying plastic chairs for Sarana elders society |  | 547 B Kongasyaya |  | CD | cb | Goods |  | 9700 | 10000 | 9700 | 10 plastic chairs with arm | [9 empty] | 1 | 60
44 | 3 |  | Supplying electrocity for muslim cemetry at madampe |  | 537 Marakkalagama | 10565 | EL | El | Goods |  | 98284 | 100000 | 98284 | Orange 15A One way Swich 04/ 1/12 GI pipes 07/ 2˝ GI pipes 04/100w steet lampe 10 | [9 empty] | 1 | 350 | 98284
45 | 4 |  | Supplying chairs for suhada funarulaid society at Helenawaththa |  | 543 Kudirippuwa | 10560 | CD | cb | Goods |  | 9700 | 10000 | 9700 | 10 plastic chairs with arm | [9 empty] | 1 | 200
46 | 5 |  | Supplying chairs and hut for funarulaid and welfaire society |  | 542 A Galmuruwa South | 10576 | CD | cb | Goods |  | 29100 | 30000 | 29100 | Nilkamal armless chairs 30 | [9 empty] | 1 | 100
47 | 6 |  | Supplying chairs for Ekamuthu funarulaid society at KAchchakaduwa |  | 544 A Kachchakaduwa |  | CD | cb | Goods |  | 9700 | 10000 | 9700 | [10 empty] | 1 | 130
48 | 7 |  | Supplying cooking wears for Silwagate samagai rural development society . |  | 533 Uraliyagara | 10571 | CD | cb | Goods |  | 18500 | 15000 | 15000 | 10kg pot 01/07kg pots 02/ 05 kg pots 02 | [9 empty] | 1 | 129
49 | 8 |  | Supplying elecrocity and water for the uraliya Sewapiyasa |  | 551 Uraliya | 10556 | EL | El | Goods |  | 19765.16 | 25000 | 19765.16 | connection | [9 empty] | 1
50 | 9 |  | Supplying chairs for Ekamuthu elders society |  | 541 A Suduwella |  | CD | cb | Goods |  | 9700 | 10000 | 9700 | 10 Nilkamal chairs | [9 empty] | 1 | 75
51 | 10 |  | Supplying chairs for Palawaththa Prajasanwardana sanwidanaya |  | 533 Uraliyagara | 10571 | CD | cb | Goods |  | 14550 | 15000 | 14550 | 15 Nilkamal chairs | [9 empty] | 1 | 84
52 | 11 |  | Supplying a tub well for CH/ GALMURUWA KANITU VIDUHALA |  | 542 A Galmuruwa South | 10576 | WS | W | Goods |  | 209000 | 200000 | 194000 | tube well 01 | [9 empty] | 1 | 282 | 194000
53 | 12 |  | Supplying a hut for Eksath funarulaid welfaire society at Egodakudirippuwa |  | 543 Kudirippuwa | 10560 | CD | cb | Goods |  | 56000 | 30000 | 30000 | 15x15 hut | [9 empty] | 1 |  | 30000
54 | 13 |  | Completing the balance work of SEWAPIYASA at Idigaswila |  | Idigaswila | 1187 | CD | S | Construction |  | 221377.28 | 200000 | 194000 | [10 empty] | 1 | 459 | 194000
55 | 14 |  | Supplying goods for registered societies |  | Divisional Secretariat | 1187 | CD | cb | Goods |  | 196818 | 200000 | 196818 | 100 plates /141 plastic chairs | [9 empty] | 1 |  | 196818
56 | 15 |  | Supplying sport goods for registered sport clubs |  | Divisional Secretariat | 1187 | CD | SPO | Goods |  | 99200 | 100000 | 99200 | Volly balls 17 / volly ball net 10 | [9 empty] | 1 | 262 | 99200
57 | 16 |  | Supplying chairs for Methodistha Church at Sembokattiya |  | 553 Sembukattiya | 10555 | CD | R | Goods |  | 49878 | 50000 | 49878 | 51plastic chairs with arm | [9 empty] | 1 | 125 | 49878
58 | 17 |  | Supplying chairs for Samurdi Samithiya |  | 547 Mahagama south | 10536 | CD | cb | Goods |  | 9700 | 10000 | 9700 | 10 plastic chairs | [9 empty] | 1 | 85
59 | 18 |  | Supplying chairs for Liyapubudu Rural Development society |  | 541 Mugunuwatawana | 10578 | CD | cb | Goods |  | 9700 | 10000 | 9700 | Nilkamal armless chairs 10 | [9 empty] | 1 | 15
60 | 19 |  | Supplying chairs for Community Hall at Gurumudunkele |  | 541 Mugunuwatawana | 10579 | CD | cb | Goods |  | 14550 | 15000 | 14550 | Nilkamal armless chairs 15 | [9 empty] | 1 | 200
61 | 20 |  | Supplying musical equipment for Athuwana Vidyalaya |  | 547C Athuwana | 10534 | CD | e | Goods |  | 47750 | 50000 | 47750 | base drum 01/side drum 03/melodica 04 | [9 empty] | 1 | 123
62 | 21 |  | Supplying a water tank for sri genodayaramaya Viharaya |  | 540 A Pukulama |  | CD | R | Goods |  | 9700 | 10000 | 9700 | 2 water tanks | [9 empty] | 1 | 980
63 | 22 |  | Supplying cooking wears for 553 Uraliyagar elders society |  | 533 Uraliyagara | 10571 | CD | cb | Goods |  | 11400 | 10000 | 10000 | a cooking wear for 30 kg | [9 empty] | 1
64 | 23 |  | Supplying chairs for ch/Madagama centrel college |  | 546 A Madagama |  | CD | e | Goods |  | 49896 | 50000 | 49896 | Damro plastic chairs 42 | [9 empty] | 1 | 1400
65 | 24 |  | Supplying chairs for ch/Herath Gunarathna Vidyalaya |  | 543 Kudirippuwa | 10560 | CD | e | Goods |  | 49608 | 50000 | 49608 | Damro plastic chairs 53 | [9 empty] | 1 | 847 | 49608
66 | 25 |  | Supplying water for Nila Sewana Karyalaya at PATTIYAGAMA |  | 535 Pattiyagama |  | WS | W | WS |  | 22912 | 20000 | 19400 | conection | [9 empty] | 1 |  | 19400
67 | 26 |  | Repairing Community Hall at Walahena |  | 556 A Walahena |  | CD | C | Construction |  | 221377.28 | 200000 | 194000 | [10 empty] | 1 | 614 | 194000
68 | 1 | Hon.M.P. Arundika Fernando. | supplying net and iron pipes for fence ground of V-SIX Sport club at Thaniwallagama |  | 540 Thaniwellegama |  | CD | SPO | Goods |  | 95500 | 100000 | 95500 | 2" pakistan GI Pipes 09/ 3/4 GI Pipes 14 / 5´ net rolle 01 | [9 empty] | 1 | 100 | 95500
69 | 2 |  | Supplying a 15 X15 hut for funarulaid welfaire society at Pukulama |  | 540 A Pukulama |  | CD | cb | Goods |  | 99318 | 100000 | 99318 | 15x15 hut 01/ 31 plastic chairs | [9 empty] | 1 |  | 69000 | 69000
70 | 3 |  | Completing the balance work of Multi purpose Building of Sri Manikbodi Viharaya at Rathmallagara | 545 ඒ රත්මල්අගාර | 545 A Rathmallagara |  | CD | C | Construction |  | 194415.92 | 200000 | 164909.85 | [10 empty] | 1 |  | 164909.85 | 30318
71 | 4 |  | For balance work of Community Hall at Galahitiyawa , Ranawarapitiya 1st lane |  | 534 C Galahitiyawa | 10563 | CD | C | Construction |  | 194712.5 | 200000 | 190118.71 | [10 empty] | 1 | 100 | 190118.71 | 99318
72 | 5 |  | Supplying a 15*10 hut for Kajugahawaththa welfaire society at Karukkuwatawana | 200000 | 552 Karukkuwatawana |  | CD | cb | Goods |  | 50000 | 50000 | 50000 | 15*10 hut | [9 empty] | 1 |  | 50000
73 | 6 |  | Supplying chairs for Hadabandaragama Nawa wasana sports club |  | 534 A Pothuwila |  | CD | cb | Goods |  | 49878 | 50000 | 49878 | 51plastic chairs | [9 empty] | 1 |  | 49878
74 | 7 |  | Supplying chairs for Eksath funarulaid societat athuwana |  | 547C Athuwana | 10534 | CD | cb | Goods |  | 39120 | 40000 | 39120 | 40plastic chairs | [9 empty] | 1 |  | 39120
75 | 8 |  | Supplying a weight set for Sithumina Kayawardana sport club |  | Mahagama |  | CD | SPO | Goods |  | 49900 | 50000 | 49900 | 2 Excercis machine | [9 empty] | 1 |  | 49900
76 | 9 |  | Supplying plastic chairs for Sakthi Prajamangala society at Kachchakaduwa |  | 544 A Kachchakaduwa |  | CD | cb | Goods |  | 24336 | 25000 | 24336 | Damro plastic arm chairs 26 | [9 empty] | 1 | 25
77 | 10 |  | Providing side pillars to elle sports for Nawakatharu sports club at Heennagaraya |  | 551A Heennagara | 10558 | CD | SPO | Goods |  | 19600 | 15000 | 15000 | 1½'' pakisthan galwernice pipes 2/2'pakisthan galwernice pipe' | [9 empty] | 1 | 30
78 | 11 |  | Supplying plastic chairs for Eksath funarulaid welfaire society at Egodakudirippuwa |  | 543 Kudirippuwa | 10560 | CD | cb | Goods |  | 24975 | 25000 | 24975 | Damro plastic armless chairs 25 | [9 empty] | 1 | 250
79 | 12 |  | Supplying plastic chairs for Eksath THREE RODARATHA Sangamaya at Kudabingiriya Madagama |  | 546 Kudabingiriya |  | CD | cb | Goods |  | 24336 | 25000 | 24336 | Damro plastic armless chairs 26 | [9 empty] | 1 | 80
80 | 13 |  | Supplying plastic chairs for Suwashakthi sport club at Grasland waththa ,No 04 |  | 542 A Galmuruwa South | 10576 | CD | cb | Goods |  | 24450 | 25000 | 24450 | plastic arm chairs 25 | [9 empty] | 1 | 125
81 | 14 |  | Supplying net for Fixing net frem for Hadabandaragama Dewalaya |  | 545 B Rathnagiriya |  | CD | R | Goods |  | 35975 | 50000 | 35975 | 2˝ x 2 sQure net rolle 02/ 1" x 1" box bar 11 | [9 empty] | 1 | 60 | 35975
82 | 1 | Hon.M.P.Hector Appuhami | Supplying a table with cupboard for funarulaid society at Sembukattiya |  | 553 Sembukattiya | 10555 | CD | cb | Goods |  | 20000 | 20000 | 20000 | 01 table with cupboard | [9 empty] | 1 |  | 20000
83 | 2 |  | Supplying a cupboard for Sewana Elder's society at Hadabandaragama |  | 534 A Pothuwilla |  | CD | cb | Goods |  | 19900 | 20000 | 19900 | 01 cupboard | [9 empty] | 1 |  | 19900
84 | 3 |  | Supplying plates and glass for Rural Development society at Pattiyagama |  | 535 Pattiyagama |  | CD | cb | Goods |  | 29921 | 30000 | 29921 | 83 plates / 14 glass sets | [9 empty] | 1 |  | 29921
85 | 4 |  | Supplying a Hut for Meththa eldre's society at Thaniwellagama |  | 540 Thaniwellegama |  | CD | cb | Goods |  | 25000 | 25000 | 25000 | 01 hut | [9 empty] | 1 |  | 25000
86 | 5 |  | Supplying a Hut for Ekamuthu funarulaid society at Egodayagama |  | 535 A Egodayagama |  | CD | cb | Goods |  | 25000 | 25000 | 25000 | 01 hut | [9 empty] | 1 |  | 25000
87 | 6 |  | Supplying chairs for Rural Development society at Panirendawa |  | 546 B Panirendawa |  | CD | cb | Goods |  | 19560 | 20000 | 19560 | 20 plastic chairs | [9 empty] | 1 |  | 19560
88 | 7 |  | Supplying chairs for Pathima funarulaid society at Madagama |  | 546 A Madagama |  | CD | cb | Goods |  | 18700 | 20000 | 18700 | 11 plastic chairs | [9 empty] | 1 |  | 18700
89 | 8 |  | Supplying chairs for Parami elder's society at Pallakele |  | 543 A Pallakele |  | CD | cb | Goods |  | 19656 | 20000 | 19656 | 21 damro armless chairs | [9 empty] | 1 |  | 19656
90 | 9 |  | Supplying chairs for sri Punnawardanaramaya funarulaid society at Madagama |  | 546 Kudabingiriya |  | CD | cb | Goods |  | 19980 | 20000 | 19980 | 20 damro chairs | [9 empty] | 1 |  | 19980
91 | 10 |  | Supplying a Hut for DELENA THARU Pre school at Issanmadilla |  | 554 Karrukkuwa |  | CD | e | Goods |  | 35000 | 35000 | 35000 | 10*10 hut 01 | [9 empty] | 1 | 25 | 35000
|  |  | TOTAL | [8 empty] | 5649000 | 5464097.05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 17159 | 3988771.54
|  | Description for rating |  |  |  | Rates | Percentage Ranges
|  | Estimate is being / to be prepared and initial works started |  |  |  | A | (0 - 5)% |  |  |  |  | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared,
B-2= Quotation / Bid called, B-3= Quotation / Bid Received , B-4= Contract Awarded
|  | Constructions: B - 1 = Estimates approved / Bid documents prepared, B - 2 = Quotation / Bid called B - 3 = Quotation / Bid Received B - 4 = Contract Awarded. (25% completed) Other : Identified Institutions / CBO's to provide Goods/ Instruments Obtain required list of goods, Estimated prepared |  |  |  | B | (6 - 25)% |  |  |  |  | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain
required list of goods, Estimated prepared
|  | Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments |  |  |  | C | (26 - 40)% |  |  |  |  | C - For Constructions : Start construction work ,40% completed, Other : placed order for goods
|  | Constructions : 60% Completed Other : Received goods / instruments as per the order |  |  |  | D | (41 - 60)% |  |  |  |  | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
|  | Constructions : 80% Completed Other : Received goods / instruments as per the order |  |  |  | E | (61 - 80)% |  |  |  |  | E - For Constructions 80% completed Other : Received goods /instruments as per the order
|  | Constructions : 99% Completed Other : Completed lists of goods to be given to beneficiaries |  |  |  | F | (81 - 99)% |  |  |  |  | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
|  | Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs |  |  |  | G | 100% |  |  |  |  | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
නොකෙරෙන ව්‍යාපෘති
|  |  | For Ranawiru Smarakaya |  | 537 A Mahabaddegama |  | CD |  | Construction |  |  | 300000
|  |  | Building sub post office building at Thabagalla |  | 557 Tabagalla |  | CD |  | Construction |  |  | 500000
|  |  | Developing the Grasland Wattha Main Road at Galmuruwa South |  | 542 A Galmuruwa South |  | RA |  | Construction |  |  | 500000
|  |  | Supplying plastic chairs and a 15*20 hut for EKSATH funarulaid society at Galmuruwa South |  | 542 A Galmuruwa South |  | CD |  | Goods |  |  | 150000
[12 empty] | 1450000 |  | 1475325.51
3988771.54
5464097.05