## Sheet1
Gamperaliya- Rapid Rural Development Programme - 2019
Physical and Financial Progress of the Month of 30rd November
District : Puttalam
No |  | Name of the Project | GN Division | Sector * | Name of Minister / Member of Parliament/ Officer who proposed the project | Length(k.m/m.)/ Area (/sq.m.) | Allocation | Approved Amount (Rs, Mn.) | Implementing Agency | Name of the Contractor/ Society | [11 empty] | No. of Beneficiaries | BEFOR | AFTER | COMPLTED
Physical **
[11 empty] | Expenditure (Rs. Mn.) | A | B |  |  |  | C | D | E | F | G
[13 empty] | B1 | B2 | B3 | B4
1 | 1 | Developing "Palawaththa 3 rd " road at Uraliyagara | 533 Uraliyagara | RA | HON.MP.Mr.SANTHA SISIRA KUMARA ABESEKARA |  | 500000 |  |  | Uraliyagara elders socity,Uraliyagara, madampe | 485000 | [9 empty] | 1 | 280
2 | 2 | Developing "kalyaniwathta " road at Uraliyagara |  |  |  |  | 500000 |  |  | Uraliyagara elders socity,Uraliyagara, madampe | 484381.41 | [9 empty] | 1 | 25
3 | 3 | Developing "Palawaththa 3 rd " road at Uraliyagara |  |  |  |  | 500000 |  |  | Samagi rural development socity, silvergate,madampe | 485000 | [9 empty] | 1 | 280
4 | 4 | Developing "Tharanawaththa " road at Malalawagara | 533 A Mellawagara |  |  |  | 500000 |  |  | Sahana Elders Socity "Mallawagara" | 484939.22 | [9 empty] | 1 | 21
5 | 5 | Developing "Shantha Anthony " road at Malalawagara |  |  |  |  | 500000 |  |  | Sahana Elders Socity "Mallawagara" | 485000 | [9 empty] | 1 | 183
6 | 6 | Developing "Mrs.Himali Jayawardan's " road at Irattakulama North | 534 Irattakulama North |  |  |  | 1000000 |  |  | Rural developin socity, Irattakulama, Madampe | 636621.09 | [9 empty] | 1 | 115
7 | 7 | Developing "Potuwila waththa Mr.Tilaka's home " road at Potuwila | 534 A Pothuvila |  |  |  | 1000000 |  |  | Sewana Elders Socity"Pothuwila" | 970000 | [9 empty] | 1 | 8
8 | 8 | Developing "Kammala " road at Irattakulama south | 534 B Irattakulama South |  |  |  | 1000000 |  |  | Sarana elders socity, Irattakulama, madampe | 650120.43 | [9 empty] | 1 | 30
9 | 9 | Developing "Mrs.Anoja's home " road at Galahitiyawa | 534 C Galahitiyawa |  |  |  | 1000000 |  |  | Eksath elders socity,Galahitiyawa | 970000 | [9 empty] | 1 | 250
10 | 10 | Developing "Infornt of the Comminity hall " road at Erunvila | 534 D Erunvila |  |  |  | 1000000 |  |  | Sanasuma Elders socity "Erunwila" | 970000 | [9 empty] | 1 | 30
11 | 11 | Developing "Shantha Sebasthiyan " road at Pattiyagama | 535 Pattiyagama |  |  |  | 1000000 |  |  | Rural development socityPattiyagama, Madampe | 970000 | [9 empty] | 1 | 420
12 | 12 | Developing "Access " road at Egodayagama | 535 A Egodayagama |  |  |  | 1000000 |  |  | Ekamuthu elders socity,Egodayagama | 753546.82 | [9 empty] | 1 | 320
13 | 13 | Developing "Mr.Shaliy's home " road at Ihalagama | 536 Ihalagama |  |  |  | 1000000 |  |  | Ekamuthu Elders socity "Ihalagama" | 466740.67 | [9 empty] | 1 | 25
14 | 14 | Developing Access road at Marakkalagama | 537 Marakkalagama |  |  |  | 1096970.72 |  |  | Mahabaddegama thaniyawallaba elders socity, old toun ,Madampe | 1060316.69 | [9 empty] | 1 | 1000
15 | 15 | Developing Access road at Marakkalagama | 537 A Mahabaddegama |  |  |  | 1097000 |  |  | Mahabaddegama thaniyawallaba elders socity, old toun ,Madampe | 1060641.69 | [9 empty] | 1
16 | 16 | Developing Access road at Nelumpokuna | 540 Nelumpokuna |  |  |  | 1000000 |  |  | Nelumpokuna elders socity, Nelumpokuna, Madampe | 970000 | [9 empty] | 1 | 160
17 | 17 | Developing Access road at Puukkulama | 540 A Puukkulama |  |  |  | 1000000 |  |  | Sawiya elders socity, pukulama | 965539.55 | [9 empty] | 1 | 110
18 | 18 | Developing Access road at Thaniwellagama | 540 B Thaniwellagama |  |  |  | 1000000 |  |  | Meththa elders Socity "Thaniwellagama" | 970000 | [9 empty] | 1 | 114
19 | 19 | Developing "Koongaha waththa" road at Mugunuwatawana | 541 Mugunuwatawana |  |  |  | 1000000 |  |  | Ekasath Samadi Elders Socity "Mugunuwatawana" | 970000 | [9 empty] | 1 | 13
20 | 20 | Developing "Rathnayaka " Mawatha at Suduwella | 541 A Suduwella |  |  |  | 1000000 |  |  | Ekamuthu elders socity, Suduwella | 969277.03 | [9 empty] | 1 | 10
21 | 21 | Developing 5th Road at Helenawaththa | 543 Kudeerippuwa |  |  |  | 1000000 |  |  |  | 964201.95 | [9 empty] | 1 | 850
22 | 22 | Developing '' Nawa Janapadaya'' road at Pallakalle | 543 A Pallakalle |  |  |  | 1000000 |  |  |  | 970000 | [9 empty] | 1 | 216
23 | 23 | Developing '' Mr.Thilaka Rathna 's home '' road at Pallakalle |  |  |  |  | 1000000 |  |  | Parami elders socity, Pallakaie,Galmuruwa | 970000 | [9 empty] | 1 | 116
24 | 24 | Developing main road at Kachchakaduwa | 544 A Kachchakaduwa |  |  |  | 1000000 |  |  | Maithrr elders socity "Kachhchakaduewa" | 970000 | [9 empty] | 1 | 1500
25 | 25 | Developing "cemetery " road at Nankadawara | 545 Nankadawara |  |  |  | 1000000 |  |  | Eksath Govi Sanvidanaya"Nankadawara" | 970000 | [9 empty] | 1 | 270
26 | 26 | Developing "3rd " road at Rathnagiriya | 545 B Rathnagiriya |  |  |  | 1000000 |  |  | Rural divelopmen socity "Rathnagiriya" | 970000 | [9 empty] | 1 | 25
27 | 27 | Developing "Kohomba Hena Pre school " road at Kudabingiriya | 546 Kudabingiriya |  |  |  | 1000000 |  |  | Eksath Elders socity "Kudabingiriya" | 970000 | [9 empty] | 1 | 400
28 | 28 | Developing "Near the Pre school " road at Madagama | 546 A Madagama |  |  |  | 500000 |  |  | Suwashakthi Elders Socity , Thambagalla waththa, panirendawa | 485000 | [9 empty] | 1 | 230
29 | 29 | Developing "Thambagalla Waththa " road at Madagama |  |  |  |  | 500000 |  |  | Sewashanthi elders socity, Thambagallawaththa,Panirendawa | 485000 | [9 empty] | 1 | 50
30 | 30 | Developing Access road at Mahagama North | 547 A Mahagama North |  |  |  | 1000000 |  |  | Sarana elders socity,dakunu mahagama, Mugunuwatawana | 969845.19 | [9 empty] | 1 | 120
31 | 31 | Developing " Near the Mr.Noyel's home " road at Uraliya | 551 Uraliya |  |  |  | 1000000 |  |  | ekamuthu elders socity, Uraliya, madampe | 890690.25 | [9 empty] | 1 | 10
32 | 32 | Developing " Karanwaththa " road at Heennagara | 551 A Heennagara |  |  |  | 1000000 |  |  | eksath elders socity, Heenagara,panirendawa | 970000 | [9 empty] | 1 | 150
33 | 33 | Developing "Hena " road at Karukuwatawana | 552 Karukkuwatawana |  |  |  | 1000000 |  |  | Sarana elders socity, Karukkuwatawana, madampe | 970000 | [9 empty] | 1 | 40
34 | 34 | Developing "School left side " road at Sembukattiya | 553 Sembukattiya |  |  |  | 1000000 |  |  | Asarana Sarana Elders Socity ,Sembukattiya | 970000 | [9 empty] | 1 | 5
35 | 35 | Developing "Dewala " road at karukkuwa | 554 Karukkuwa |  |  |  | 1000000 |  |  | Eksath Elders Socity"Karukkuwa" | 970000 | [9 empty] | 1 | 25
36 | 36 | Developing Play ground road at Hareendragama | 554 A Hareendragama |  |  |  | 1000000 |  |  | Janashakthi Rural developing socity, Harindragama,madampe | 774772.51 | [9 empty] | 1 | 25
37 | 37 | Developing "Pitawalayagama Walahena" road at Ponnankanniya | 555 A Ponnankanniya |  |  |  | 1000000 |  |  | SuwasawiyaEksath elders socity, Miriswaththa,Walahena, | 942901.86 | [9 empty] | 1 | 300
38 | 38 | Developing "Pitawalayagama Walahena" road at Walaheena | 556 A Walaheena |  |  |  | 1000000 |  |  | SuwasawiyaEksath elders socity, Miriswaththa,Walahena, | 970000 | [9 empty] | 1 | 300
39 | 39 | Developing "Petti Bokkuwa " at Walaheena |  |  |  |  | 2000000 |  |  |  | 1839014.22 | 1839014.22 |  |  |  |  | 1
40 | 40 | Developing "Thalgasduwa Mr.Nalaka's home road" at Manakkulama | 556 B Manakkulama |  |  |  | 1000000 |  |  | Manakkulama Rural Development Socity | 970000 | [9 empty] | 1 | 34
41 | 41 | Developing "Karawita Kohaba Waththa main Road" at Manakkulama |  |  |  |  | 1500000 |  |  |  | 1455000 | [9 empty] | 1
42 | 42 | Developing "Ihala Thambagalla road" at Thambagalla | 557 Thambagalla |  |  |  | 1000000 |  |  | Shakthi eldes Sosity"Thambagalla" | 970000 | [9 empty] | 1 | 38
43 | 43 | Developing "Ahatu gaha waththa road" at Dematapitiya | 557 A Dematapitiya |  |  |  | 1000000 |  |  | Ekamuthu Elders Socity "Dematapitiya" | 970000 | [9 empty] | 1 | 82
44 | 44 | Developing "3 rd road" at Thambagalla waththa | 557 B Thambagalla waththa |  |  |  | 500000 |  |  | Wimukthi elders socity, Panirendawa | 485000 | [9 empty] | 1 | 13
45 | 45 | Developing "4 th road" at Thambagalla waththa |  |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1 | 17
46 | 46 | Developing "Korasa Mawatha " at Thambagalla west | 557 C Thambagalla west |  |  |  | 1000000 |  |  | Suwashakthi Elders Socity , Thambagalla | 970000 | [9 empty] | 1 | 400
47 | 47 | Developing "Pahala Waththa 7 th road " at Pambala North | 560 Pambala North |  |  |  | 1000000 |  |  |  | 969066.74 | [9 empty] | 1 | 12
48 | 48 | Developing "Access road " at Kogasyaya | Koongasyaya |  |  |  | 1000000 |  |  | Sarana elders socity, kongasyaya, mugunuwatawana | 970000 | [9 empty] | 1 | 152
49 | 49 | Developing ''Mr. Samantha's home road " at Pambala North South | 560 A Pambala South |  |  |  | 1000000 |  |  | Elders socity, Pambala, Kakkapalliya | 853624.64 | [9 empty] | 1 | 7
50 | 50 | Developing Agara Road at Irattakulama | Irattakulama North | [6 empty] | Sarana elders socity, Ihalagama,Madampe | 333378.91 | [9 empty] | 1 | 8
51 | 51 | Developing Gramanilladari mahathage home's Road | Irattakulama south | [6 empty] | Sarana elders socity, Irattakulama, madampe | 315250 | [9 empty] | 1 | 23
52 | 52 | Developing wendesiwaththa 1 st Road | Ihalagama | [7 empty] | 503259.33 | [9 empty] | 1
53 | 53 | Developing "Access " road at Walahena | Walahena |  |  |  | 1000000 |  |  |  | 963085.01 | [9 empty] | 1
54 | 54 | Developing "Access " road at Rathnagiriya | Rathnagiriya |  |  |  | 1000000 |  |  |  | 964015.71 | [9 empty] | 1
55 | 55 | Developing "Access " road at Galmuruwa South | Galmuruwa South |  |  |  | 1000000 |  |  |  | 963207.3 | [9 empty] | 1
56 | 56 | Developing "Henyaya " road at Sembukattiya | Sembukattiya |  |  |  | 1000000 |  |  |  | 964008 | [9 empty] | 1
57 | 57 | Developing "Ihala thambagalla " road at Tambagalla | Tambagalla |  |  |  | 1000000 |  |  | Shakthi elders socity,Thambagalla,Kakkapalliya | 964022.13 | [9 empty] | 1 | 33
58 | 58 | Developing "Manakkulama kate handiya " road at Manakkulam | Manakkulama |  |  |  | 500000 |  |  |  | 479030.75 | [9 empty] | 1
59 | 1 | Implimentation of drinking water project for Rathmallagara | 545 A Rathmallagara | WS |  |  | 2000000 |  |  |  | 918828.18 | [7 empty] | 1
60 | 2 | Implimentation of drinking water project for Panirendawa | 546 B Panirendawa |  |  |  | 2000000 |  |  |  | 549454.19 | [7 empty] | 1
61 | 3 | Implimentation of drinking water project for Mahagama North | 547 Mahagama North |  |  |  | 2000000 |  |  |  | 1027961.02 | [7 empty] | 1 |  |  | 310
62 | 4 | Implimentation of drinking water project for Galmuruwa south | 542 A Galmuruwa south |  |  |  | 2000000 |  |  |  | 1066098.85 | [7 empty] | 1 |  |  | 319
63 | 5 | Implimentation of drinking water project for Galmuruwa North | Galmuruwa North |  |  |  | 2000000 |  |  |  | 1035001.86 | [7 empty] | 1
64 | 6 | Implimentation of drinking water project for Athuwana | 547 C Athuwana |  |  |  | 2000000 |  |  |  | 1066098.85 | [7 empty] | 1
65 | 7 | Implimentation of drinking water project for Idigaswila | 557 D Idigaswila |  |  |  | 2000000 |  |  |  | 1035001.86 | [7 empty] | 1
66 | 8 | Implimentation of drinking water project for Henapola | 542 Henapola |  |  |  | 2000000 |  |  |  | 1035001.86 | [7 empty] | 1
67 | 9 | Implimentation of drinking water project for Uraliya | Uraliya |  |  |  | 1000000 |  |  |  | 851368.65 | [9 empty] | 1
68 | 1 | Developing "Sri Pushparama Temple " at Kachchakaduwa | 544 A Kachchakaduwa | RC |  |  | 500000 |  |  | Pushparama Dayaka sabawa, Kachchakaduwa, Dummalasoriya | 445799.52 | [9 empty] | 1 | 89
69 | 2 | Developing "Sri Sunandarama Temple " at Galmuruwa south | 544 Galmuruwa south |  |  |  | 1000000 |  |  | Sri Punyawardhana Dayaka sabawa,Sri sunandaramaya,Galmuruwa | 970000 | [9 empty] | 1 | 350
70 | 3 | Developing "Sri Surammyarama Temple " at Kudeerippuwa | 543 Kudeerippuwa |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
71 | 4 | Developing "Sri Samayawardanarama Temple " at Suduwella | 541 A Suduwella |  |  |  | 500000 |  |  | Sri Samayawardhanarama dayaka sabawa, Suduwella | 485000 | [9 empty] | 1 | 800
72 | 5 | Developing "Sri Niwesaramaya Temple " at Ponnankanniya | 555 A Ponnankanniya |  |  |  | 500000 |  |  | Wiharasthana karyasadana samithiya, Sri Niwesharamaya,ponnankanniya | 485000 | [9 empty] | 1 | 256
73 | 6 | Developing "Sri Suvisudharamaya Temple " at Manakkulama | 556 B Manakkulama |  |  |  | 500000 |  |  | Wiharastha dayaka sabawa, Sri wisuwiddharamaya, Manakkulama, kakkapalliya | 485000 | [9 empty] | 1 | 2000
74 | 7 | Developing "Sri Pushparamaya Temple " at Thamhagalla | 557 Thambagalla |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
75 | 8 | Developing "Sri Pushparamaya Temple " at Kudabingiriya | 546 Kudabingiriya |  |  |  | 500000 |  |  | Sri pPnyawardhana karya sadana samithiya, Sri pushparamaya,Kudabingiriya | 485000 | [9 empty] | 1 | 450
76 | 9 | Developing "Sri Pushparamaya Temple " at Uraliya | 551 Uraliya |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
77 | 10 | Developing "Sri bodi malu rajama wiharaya " at Nankadawara | 545 Nankadawara |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
78 | 11 | Developing "Sri Vijitharama Temple " at Mahagama North | 547 Mahagama North |  |  |  | 500000 |  |  | Rural development socity,MahagamaSouth, Mugunuwatawana | 483731.67 | [9 empty] | 1 | 500
79 | 12 | Developing "Sri Munindarama Temple " at Athuwana | 547 C Athuwana |  |  |  | 500000 |  |  |  | 280322.84 | [9 empty] | 1
80 | 13 | Developing "Sri Abiwanarama Temple " at Athuwana |  |  |  |  | 500000 |  |  | Upeksha elders socity,Athuwana,Mugunuwatawana | 485000 | [9 empty] | 1 | 96
81 | 14 | Developing "Sri Sugatharama Temple " at Mahagama South | 547 A Mahagama North |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
82 | 15 | Developing "Sri Sudarshanarama Temple" at Mahabadegama | 537 A Mahabaddegama |  |  |  | 500000 |  |  | Ubayartha Sadaka dayaka sabawa,Mahabaddegama | 485000 | [9 empty] | 1 | 350
83 | 16 | Developing "St . Sebasthiyan church " at Pattiyagama | 535 Pattiyagama |  |  |  | 500000 |  |  |  | 470330.53 | [9 empty] | 1
84 | 17 | Developing "Sri Jayathilinaramaya Temple " at Ihalagama | 536 Ihalagama |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
85 | 18 | Developing "Sri Subodharamaya Temple " at Galahitiyawa | 534 C Galahitiyawa |  |  |  | 500000 |  |  | Eksath Elders Socity, Galahitiyawa | 484974.5 | [9 empty] | 1 | 500
86 | 19 | Developing "Sri Dramarama Temple " at Uraliyagara | 533 Uraliyagara |  |  |  | 500000 |  |  | Wihara wardhana dayaka sabawa, madampe | 483102.12 | [9 empty] | 1 | 1050
87 | 20 | Developing "Thinipitiya wiharaya " at Mellawagara | 533 A Mellawagara |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
88 | 21 | Developing "Sri Dharmarakkitara'' Temple at Mugunuwatawana | 541 Mugunuwatawana |  |  |  | 500000 |  |  | Wihara wardhana dayaka sabawa, Sri Dhammarakkitharamaya, Mugunuwatawana,madampe | 485000 | [9 empty] | 1 | 110
89 | 22 | Developing "Sri Ghanodayarama Temple " at Puukkulama | 540 A Puukkulama |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
90 | 23 | Developing "Sri Siriwardanarama Temple" at Nelumpokuma | 540 Nelumpokuna |  |  |  | 500000 |  |  | Nelumpokuna Rural development socity, Madampe | 485000 | [9 empty] | 1 | 80
91 | 24 | Developing "Siri sumana Kusumarama Temple " at Nelumpokuna |  |  |  |  | 500000 |  |  | Sira sumana kusumarama wiharastha dayaka sabawa, Nelumpokuna, madampe | 485000 | [9 empty] | 1 | 94
92 | 25 | Developing "Sri Pushparama Temple " at Henapola | 542 Henapola |  |  |  | 500000 |  |  | Sri pushparama wiharastha dayaka sabawa, Udalawela, henepola,galmuruwa | 477718.87 | [9 empty] | 1 | 180
93 | 26 | Developing "Sri Bodirajarama Temple " at Hareendragama | 554 A Hareendragama |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
94 | 27 | Developing "Sri Somananndaramaya Temple " at Sembukattiya | 553 Sembukattiya |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
95 | 28 | Developing "Siri Sumitharama Temple " at Walaheena | 556 A Walaheena |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
96 | 29 | Developing "Madagama church " at Madagama | Madagama |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
97 | 30 | Developing "Siri Manikbodi Temple " at Rathmallagara | Rathmallagara |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
98 | 31 | Developing "Mugunuwatawana church " at Mugunuwatawana | Mugunuwatawana |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
99 | 32 | Developing "Pambala church " at Pambala | Pambala |  |  |  | 500000 |  |  |  | 476802.24 | [9 empty] | 1
100 | 33 | Developing "Hareendragama church " at Hareendragama | Hareendragama |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
101 | 34 | Developing "Galmuruwa church " at Galmuruwa | Galmuruwa North |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
102 | 35 | Developing "Rathnagiriya church " at Rathnagiriya | Rathmallagara |  |  |  | 500000 |  |  |  | 484640.84 | [9 empty] | 1
103 | 36 | Developing " Dematapitiya church " at Dematapitiya | Dematapitiya |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
104 | 37 | Developing "Koongasyaya Temple " | Koongasyaya |  |  |  | 500000 |  |  |  | 463036.98 | [9 empty] | 1
105 | 38 | Developing church at Athwana | 547 C Athuwana |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
106 | 39 | Developing church at Potuwila | Potuwila |  |  |  | 500000 |  |  |  | 479000 | [9 empty] | 1
107 | 40 | Developing church at Sembukattiya | Sembukattiya |  |  |  | 500000 |  |  |  | 485000 | [9 empty] | 1
108 | 41 | Developing church at Athwana | Atuwana |  |  |  | 300000 | [9 empty] | 1
109 | 42 | Developing "Sri Sugatharama Temple " at Mahagama South | Uthru Mahagama |  |  |  | 400000 |  |  |  | 382010.16 | [9 empty] | 1
110 | 1 | Supplying Electricity for Mr.Kasun Lakdeenu | Mahagama South | EL |  |  | 20000 |  |  |  |  | 1
111 | 2 | Supplying Electricity for Mrs.Thamara Kumari Darmasiri |  |  |  |  | 20000 |  |  |  | 18915.16 | [9 empty] | 1
112 | 3 | Supplying Electricity for Mr.Sunil Shantha |  |  |  |  | 20000 |  |  |  |  | 1
113 | 4 | Supplying Electricity for Mr.J.A.Ishan Madusanka |  |  |  |  | 20000 |  |  |  | 18915.16 | [9 empty] | 1
114 | 5 | Supplying Electricity for Mr.Wasantha Rathnasiri |  |  |  |  | 20000 |  |  |  | 18915.16 | [9 empty] | 1
115 | 6 | Supplying Electricity for Mr.Nalin Indika |  |  |  |  | 20000 |  |  |  | 19400 | [9 empty] | 1
116 | 7 | Supplying Electricity for Mr.Chinthaka Mahesh |  |  |  |  | 20000 |  |  |  |  | 1
117 | 8 | Supplying Electricity for Mr.Rohana Kumara Amarasinha |  |  |  |  | 20000 |  |  |  |  | 1
118 | 9 | Supplying Electricity for Mr.A.N.Pradeep Nilan | Galmuruwa south |  |  |  | 20000 |  |  |  |  | 1
119 | 10 | Supplying Electricity for Mrs.W.Malkanthi |  |  |  |  | 20000 |  |  |  |  | 1
120 | 11 | Supplying Electricity for Mr.A.A.Chanaka Sadun Kumara |  |  |  |  | 20000 |  |  |  | 18915.16 | [9 empty] | 1
121 | 12 | Supplying Electricity for Mr.Wajira Desappriya |  |  |  |  | 20000 |  |  |  |  | 1
122 | 13 | Supplying Electricity for Mrs.K.Chandrakanthi |  |  |  |  | 20000 |  |  |  |  | 1
123 | 14 | Supplying Electricity for Mrs.W.P.Inoka Madumali | Pallakalle |  |  |  | 20000 |  |  |  |  | 1
124 | 15 | Supplying Electricity for Mr.I.M.G.Siyantha Disanayaka | Mugunuwatawana |  |  |  | 20000 |  |  |  | 19400 | [9 empty] | 1
125 | 16 | Supplying Electricity for Mr.T.Nevil Markas |  |  |  |  | 20000 |  |  |  |  | 1
126 | 17 | Supplying Electricity for Mr.S.Udayasantha |  |  |  |  | 20000 |  |  |  |  | 1
127 | 18 | Supplying Electricity for Mr.S.G.Sisira Shantha | kachchakaduwa |  |  |  | 20000 |  |  |  | 18995.16 | [9 empty] | 1
128 | 19 | Supplying Electricity for Mr.M.P.Premasiri |  |  |  |  | 20000 |  |  |  |  | 1
129 | 20 | Supplying Electricity for Mr.A.N.Pradeep Nilan |  |  |  |  | 20000 |  |  |  |  | 1
130 | 21 | Supplying Electricity for Mrs.Ani Merry rotilda | Athwana |  |  |  | 20000 |  |  |  | 18915.16 | [9 empty] | 1
131 | 22 | Supplying Electricity for Mr.W.M.Madusanka Randika | Madagama |  |  |  | 20000 |  |  |  |  | 1
132 | 23 | Supplying Electricity for Mrs.W.A.Premawathi |  |  |  |  | 20000 |  |  |  | 18915.16 | [9 empty] | 1
133 | 24 | Supplying Electricity for Mr.H.V.Pradeep Madusanka | Rathnagiriya |  |  |  | 20000 |  |  |  | 18915.16 | [9 empty] | 1
134 | 25 | Supplying Electricity for Mr.W.S.Juud Fransis | Panirendawa |  |  |  | 20000 |  |  |  | 18915.16 | [9 empty] | 1
135 | 26 | Supplying Electricity for Mrs.R.R.M.Vindhaya Wilasani | Kudabingiriya |  |  |  | 20000 |  |  |  | 18915.16 | [9 empty] | 1
136 | 27 | Supplying Electricity for Mrs.A.Sudeepa | Puukkulama |  |  |  | 20000 |  |  |  |  | 1
137 | 1 | Repairring the pitawana at Koongasyaya Tank | Koongasyaya | MI |  |  | 500000 |  |  |  | 484456.52 | [9 empty] | 1
138 | 2 | Repairring the pitawana at Sembukattiya | Sembukattiya |  |  |  | 100000 |  |  |  |  | 1
139 | 1 | Developing "Mr.S.A.Ranjith Pramalal"s Home at Manakkulama | Manakkulama |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
140 | 2 | Developing "Mr.H.M.Kusumalatha's Home at Manakkulama |  |  |  |  | 100000 |  |  |  | 51455 | [9 empty] | 1
141 | 3 | Developing "Mrs.N.Ruupika Dilhani 's Home at Manakkulama |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
142 | 4 | Developing "Mr.W.Nalin Susantha's at Manakkulama |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
143 | 5 | Developing "Mr.M.A samantha's at Manakkulama |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
144 | 6 | Developing "Mr.Sunil Shantha's Home at Manakkulama |  |  |  |  | 100000 | 100000 |  |  | 97000 | [9 empty] | 1
145 | 7 | Dematapitiya Developing "Mr.J.A.P.Perera 's Home at Dematapitiya | Dematapitiya |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
146 | 8 | Developing "Mrs.H.A.M.Jayani Prasansa 's Home at Idigaswila | Idigaswila |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
147 | 9 | Developing "Mr.W.Jems Shelton Milroi's Home at Idigaswila |  |  |  |  | 100000 |  |  |  | 81124.4 | [9 empty] | 1
148 | 10 | Developing "Mr.W.P.Sisira 's Home at Mahagama | Mahagama South |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
149 | 11 | Developing "Mr.R.P.Ranjani 's Home at Mahagama |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
150 | 12 | Developing "Mr.H.Sugath Perera's Home at Mahagama | Mahagama North |  |  |  | 100000 |  |  |  |  | 1
151 | 13 | Developing "Mr.R.P.Lani Dammika 's Home at Mahagama |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
152 | 14 | Developing "Mr.Mikal Thamel 's Home at Pambala | Pambala |  |  |  | 100000 |  |  |  | 77925 | [9 empty] | 1
153 | 15 | Developing "Mr.T.A.Ashan Maduranga fernando's Home at Athwana | Athwana |  |  |  | 100000 |  |  |  | 95631.96 | [9 empty] | 1
154 | 16 | Developing "Mr.K.A.D.Sandeepa Pradeep's Home at Athwana |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
155 | 17 | Developing "Mr.Salinda Udayanga Kuruwita 's Home at Athwana |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
156 | 18 | Developing "Mr.M.P.D.Wiraj Kusumsiri 's Home at Athwana |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
157 | 19 | Developing "Mr. K.A. Uditha Kumarasinghe's Home at Thambagalla Batahirawaththa | Thambagalla Batahira |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
158 | 20 | Developing "Mr. H. Jayathilaka's Home at Rathmalagara | Rathmalagara |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
159 | 21 | Developing "Mrs. W. Jenat Sriyani's Home at Rathnagiriya | Rathnagiriya |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
160 | 22 | Developing "Mr. Besil Dayas's Home at Rathnagiriya |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
161 | 23 | Developing "Mrs. W. Wijesekara Home at Rathnagiriya |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
162 | 24 | Developing "Mr. Pradeep Madushanka's Home at Rathnagiriya |  |  |  |  | 100000 |  |  |  |  | 1
163 | 25 | Developing "Mrs. C.W. Sadhaya kumari's Home at Kuda Bingiriya | Kudabingiriya |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
164 | 26 | Developing "Mrs. R.M. Geetha Randeni's Home at Kuda Bingiriya |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
165 | 27 | Developing "Mr. K. Ramesh Sisil Kumara's Home at Medagama | Medagama |  |  |  | 100000 |  |  |  |  | 1
166 | 28 | Developing "Mr. W.S. Jud Fransis's Home at Panirendawa | Panirendawa |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
167 | 29 | Developing "Mrs. W.S. Seetha's Home at Panirendawa |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
168 | 30 | Developing "Mr. D.A. Nimal Hemantha's Home at Panirendawa |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
169 | 31 | Developing "Mr. W.P. Inoka Damayanthi's Home at Panirendawa |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
170 | 32 | Developing "Mr. S.P. Shantha Nandasiri's Home at Sembukattiya | Sembukattiya |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
171 | 33 | Developing "Mr. S.D. Duminda Tharanga's Home at Sembukattiya |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
172 | 34 | Developing "Mr. G.L.P. Upul Chanaka's Home at Sembukattiya |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
173 | 35 | Developing "Mr. S.Asok lumara Home at Karukkuwa | karukkuwa |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
174 | 36 | Developing "Mr. S.P. piyaedasa's Home at Karukkuwa |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
175 | 37 | Developing "Mr. N. Priyankara Silwa's Home at Karukkuwa |  |  |  |  | 100000 |  |  |  | 75923.02 | [9 empty] | 1
176 | 38 | Developing "Mr. I.M.Kasun Diludha's Home at Pambala Dakuna | Koongasyaya |  |  |  | 100000 |  |  |  | 84086.78 | [9 empty] | 1
177 | 39 | Developing "Mr. E.M.N. Rathnasiri's Home at Pothuwila | Pothuwila |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
178 | 40 | Developing "Mr. N.A. Pradeep Milan Perera's Home at Pothuwila |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
179 | 41 | Developing "Mr. S.P. Duminda Iresh Kumara's Home at Pothuwila |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
180 | 42 | Developing "Mrs. E.M. Malani Swarnalatha's Home at Kachchakaduwa | Kachchakaduwa |  |  |  | 100000 |  |  |  | 82862.5 | [9 empty] | 1
181 | 43 | Developing "Mr. R.A. Sanjaya Sadaruwan's Home at Heennagara | Heennagara |  |  |  | 100000 |  |  |  |  | 1
182 | 44 | Developing "Mrs. K. Piyaseeli's Home at Karukkuwatawana | Karukkuwatawana |  |  |  | 300000 |  |  |  | 291000 | [9 empty] | 1
183 | 45 | Developing "Mr. W.G.D. Nishantha Dayananda's Home at Uraliyagara | Uraliyagara |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
184 | 46 | Developing "Mrs. W.M. Milani Asankada Silwa's Home at Uraliyagara |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
185 | 47 | Developing "Mr. B.W.R. Pushpakumara's Home at Uraliyagara |  |  |  |  | 100000 |  |  |  |  | 1
186 | 48 | Developing "Mr. W.K. Sarath Priyalal Peris's Home at Mellawagara | Mellawagara |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
187 | 49 | Developing "Mr. S.A. Awantha's Home at Mellawagara |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
188 | 50 | Developing "Mrs. K. Isanka Sadamali's Home at Irattakulama Uthura | Irattakulama Uthura |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
189 | 51 | Developing "Mrs. K. Piyumi Nelum Sugandika's Home at Irattakulama Dakuna | Irattakulama Dakuna |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
190 | 52 | Developing "Mr. E.A.H.P. Perera's Home at Irattakulama Dakuna |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
191 | 53 | Developing "Mr. Chamila Indika Nishantha's Home at Galahitiyawa | Galahitiyawa |  |  |  | 100000 |  |  |  | 52520 | [9 empty] | 1
192 | 54 | Developing "Mr. K.H.A. Gayan Maduranga's Home at Galahitiyawa |  |  |  |  | 100000 |  |  |  |  | 1
193 | 55 | Developing "Mr. W.M. Sarath Manjula Pranandu's Home at Galahitiyawa |  |  |  |  | 100000 |  |  |  |  | 1
194 | 56 | Developing "Mrs. T.K. Nirosha Anuruddika's Home at Pattiyagama | Pattiyagama |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
195 | 57 | Developing "Mr. J.A. nilan Kumara's Home at Pattiyagama |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
196 | 58 | Developing "Mr. M.M.S. Prasanna Perera's Home at Egodayagama | Egodayagama |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
197 | 59 | Developing "Mr. M. Somalatha 's Home at Ihalagama | Ihalagama |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
198 | 60 | Developing "Mr. H.M.NaZeer's Home at Marakkalagama | Marakkalagama |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
199 | 61 | Developing "Mrs. Nadeeka Surangi's Home at Thaniwellagama | Thaniwellagama |  |  |  | 100000 |  |  |  |  | 1
200 | 62 | Developing "Mrs. Viviyan Hemalatha's Home at Thaniwellagama |  |  |  |  | 100000 |  |  |  |  | 1
201 | 63 | Developing "Mrs. S.P. Nilanthi Reeta Manel's Home at Mugunuwatawana | Mugunuwatawana |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
202 | 64 | Developing "Mrs. Sumangala Damayanthi's Home at Galmuruwa Dakuna | Galmuruwa Dakuna |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
203 | 65 | Developing "Mrs. S. Suneetha Lakmini's Home at Pallekele | Pallekele |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
204 | 66 | Developing "Mr. W.S.D. Dileep Rohan Pranandu's Home at Pallekele |  |  |  |  | 100000 |  |  |  | 97000 | [9 empty] | 1
|  | Total |  |  |  |  | 97833970.72 | 100000 | 0 | 0 | 84152801.47 | 1839039.22 | 0 | 0 | 0 | 0 | 2 | 0 | 8 | 0 | 169 | 16379 | 0 | 0 | 0
A - Estimates are being / to be prepared
B - For Constructions : B-1- Estimates Approved & Bid Documents Prepared, B-2- Quotation / Bid called, B-3- Quotation / Bid Received , B-4- Contract Awarded
Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimate prepared
C - For Constructions : Start construction work ,40% completed, Other : placed order for goods
D - For Constructions : 60% completed Other : Received goods /instruments as per the order
E - For Constructions 80% completed Other : Received goods /instruments as per the order
F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
970000
485000

## Sheet2
Gamperaliya- Rapid Rural Development Programme - 2019
Physical and Financial Progress of the Month of 30rd November
District : Puttalam
No | Name of the Project | GN Division | Allocation | Approved Amount (Rs, Mn.) | Expenditure (Rs. Mn.)
1 | Developing "Palawaththa 3 rd " road at Uraliyagara | 533 Uraliyagara | 500000 |  | 485000
2 | Developing "kalyaniwathta " road at Uraliyagara |  | 500000 |  | 484381.41
3 | Developing "Palawaththa 3 rd " road at Uraliyagara |  | 500000 |  | 485000
4 | Developing "Tharanawaththa " road at Malalawagara | 533 A Mellawagara | 500000 |  | 484939.22
5 | Developing "Shantha Anthony " road at Malalawagara |  | 500000 |  | 485000
6 | Developing "Mrs.Himali Jayawardan's " road at Irattakulama North | 534 Irattakulama North | 1000000 |  | 636621.09
7 | Developing "Potuwila waththa Mr.Tilaka's home " road at Potuwila | 534 A Pothuvila | 1000000 |  | 970000
8 | Developing "Kammala " road at Irattakulama south | 534 B Irattakulama South | 1000000 |  | 650120.43
9 | Developing "Mrs.Anoja's home " road at Galahitiyawa | 534 C Galahitiyawa | 1000000 |  | 970000
10 | Developing "Infornt of the Comminity hall " road at Erunvila | 534 D Erunvila | 1000000 |  | 970000
11 | Developing "Shantha Sebasthiyan " road at Pattiyagama | 535 Pattiyagama | 1000000 |  | 970000
12 | Developing "Access " road at Egodayagama | 535 A Egodayagama | 1000000 |  | 753546.82
13 | Developing "Mr.Shaliy's home " road at Ihalagama | 536 Ihalagama | 1000000 |  | 466740.67
14 | Developing Access road at Marakkalagama | 537 Marakkalagama | 1000000 |  | 963345.97
15 | Developing Access road at Marakkalagama | 537 A Mahabaddegama | 1000000 |  | 963641.69
16 | Developing Access road at Nelumpokuna | 540 Nelumpokuna | 1000000 |  | 970000
17 | Developing Access road at Puukkulama | 540 A Puukkulama | 1000000 |  | 965539.55
18 | Developing Access road at Thaniwellagama | 540 B Thaniwellagama | 1000000 |  | 970000
19 | Developing "Koongaha waththa" road at Mugunuwatawana | 541 Mugunuwatawana | 1000000 |  | 970000
20 | Developing "Rathnayaka " Mawatha at Suduwella | 541 A Suduwella | 1000000 |  | 969277.03
21 | Developing 5th Road at Helenawaththa | 543 Kudeerippuwa | 1000000 |  | 964201.95
22 | Developing '' Nawa Janapadaya'' road at Pallakalle | 543 A Pallakalle | 1000000 |  | 970000
23 | Developing '' Mr.Thilaka Rathna 's home '' road at Pallakalle |  | 1000000 |  | 970000
24 | Developing main road at Kachchakaduwa | 544 A Kachchakaduwa | 1000000 |  | 970000
25 | Developing "cemetery " road at Nankadawara | 545 Nankadawara | 1000000 |  | 970000
26 | Developing "3rd " road at Rathnagiriya | 545 B Rathnagiriya | 1000000 |  | 970000
27 | Developing "Kohomba Hena Pre school " road at Kudabingiriya | 546 Kudabingiriya | 1000000 |  | 970000
28 | Developing "Near the Pre school " road at Madagama | 546 A Madagama | 500000 |  | 485000
29 | Developing "Thambagalla Waththa " road at Madagama |  | 500000 |  | 485000
30 | Developing Access road at Mahagama North | 547 A Mahagama North | 1000000 |  | 969845.19
31 | Developing " Near the Mr.Noyel's home " road at Uraliya | 551 Uraliya | 1000000 |  | 890690.25
32 | Developing " Karanwaththa " road at Heennagara | 551 A Heennagara | 1000000 |  | 970000
33 | Developing "Hena " road at Karukuwatawana | 552 Karukkuwatawana | 1000000 |  | 970000
34 | Developing "School left side " road at Sembukattiya | 553 Sembukattiya | 1000000 |  | 970000
35 | Developing "Dewala " road at karukkuwa | 554 Karukkuwa | 1000000 |  | 970000
36 | Developing Play ground road at Hareendragama | 554 A Hareendragama | 1000000 |  | 774772.51
37 | Developing "Pitawalayagama Walahena" road at Ponnankanniya | 555 A Ponnankanniya | 1000000 |  | 942901.86
38 | Developing "Pitawalayagama Walahena" road at Walaheena | 556 A Walaheena | 1000000 |  | 970000
39 | Developing "Petti Bokkuwa " at Walaheena |  | 2000000 |  | ගෙවිම් කර නැත
40 | Developing "Thalgasduwa Mr.Nalaka's home road" at Manakkulama | 556 B Manakkulama | 1000000 |  | 970000
41 | Developing "Karawita Kohaba Waththa main Road" at Manakkulama |  | 1500000 |  | 1455000
42 | Developing "Ihala Thambagalla road" at Thambagalla | 557 Thambagalla | 1000000 |  | 970000
43 | Developing "Ahatu gaha waththa road" at Dematapitiya | 557 A Dematapitiya | 1000000 |  | 970000
44 | Developing "3 rd road" at Thambagalla waththa | 557 B Thambagalla waththa | 500000 |  | 485000
45 | Developing "4 th road" at Thambagalla waththa |  | 500000 |  | 485000
46 | Developing "Korasa Mawatha " at Thambagalla west | 557 C Thambagalla west | 1000000 |  | 970000
47 | Developing "Pahala Waththa 7 th road " at Pambala North | 560 Pambala North | 1000000 |  | 969066.74
48 | Developing "Access road " at Kogasyaya | Koongasyaya | 1000000 |  | 970000
49 | Developing ''Mr. Samantha's home road " at Pambala North South | 560 A Pambala South | 1000000 |  | 853624.64
50 | Developing Agara Road at Irattakulama | Irattakulama North |  |  | 333378.91
51 | Developing Gramanilladari mahathage home's Road | Irattakulama south |  |  | 315250
52 | Developing wendesiwaththa 1 st Road | Ihalagama |  |  | 503259.33
53 | Developing "Access " road at Walahena | Walahena | 1000000 |  | 963085.01
54 | Developing "Access " road at Rathnagiriya | Rathnagiriya | 1000000 |  | 964015.71
55 | Developing "Access " road at Galmuruwa South | Galmuruwa South | 1000000 |  | 963207.3
56 | Developing "Henyaya " road at Sembukattiya | Sembukattiya | 1000000 |  | 964008
57 | Developing "Ihala thambagalla " road at Tambagalla | Tambagalla | 1000000 |  | 964022.13
58 | Developing "Manakkulama kate handiya " road at Manakkulam | Manakkulama | 500000 |  | 479030.75
59 | Implimentation of drinking water project for Rathmallagara | 545 A Rathmallagara | 2000000 |  | 918828.18
60 | Implimentation of drinking water project for Panirendawa | 546 B Panirendawa | 2000000 |  | 549454.19
61 | Implimentation of drinking water project for Mahagama North | 547 Mahagama North | 2000000 |  | 1027961.02
62 | Implimentation of drinking water project for Galmuruwa south | 542 A Galmuruwa south | 2000000 |  | 1066098.85
63 | Implimentation of drinking water project for Galmuruwa North | Galmuruwa North | 2000000 |  | 1035001.86
64 | Implimentation of drinking water project for Athuwana | 547 C Athuwana | 2000000 |  | 1066098.85
65 | Implimentation of drinking water project for Idigaswila | 557 D Idigaswila | 2000000 |  | 1035001.86
66 | Implimentation of drinking water project for Henapola | 542 Henapola | 2000000 |  | 1035001.86
67 | Implimentation of drinking water project for Uraliya | Uraliya | 1000000 |  | 851368.65
68 | Developing "Sri Pushparama Temple " at Kachchakaduwa | 544 A Kachchakaduwa | 500000 |  | 445799.52
69 | Developing "Sri Sunandarama Temple " at Galmuruwa south | 544 Galmuruwa south | 1000000 |  | 970000
70 | Developing "Sri Surammyarama Temple " at Kudeerippuwa | 543 Kudeerippuwa | 500000 |  | 485000
71 | Developing "Sri Samayawardanarama Temple " at Suduwella | 541 A Suduwella | 500000 |  | 485000
72 | Developing "Sri Niwesaramaya Temple " at Ponnankanniya | 555 A Ponnankanniya | 500000 |  | 485000
73 | Developing "Sri Suvisudharamaya Temple " at Manakkulama | 556 B Manakkulama | 500000 |  | 485000
74 | Developing "Sri Pushparamaya Temple " at Thamhagalla | 557 Thambagalla | 500000 |  | 485000
75 | Developing "Sri Pushparamaya Temple " at Kudabingiriya | 546 Kudabingiriya | 500000 |  | 485000
76 | Developing "Sri Pushparamaya Temple " at Uraliya | 551 Uraliya | 500000 |  | 485000
77 | Developing "Sri bodi malu rajama wiharaya " at Nankadawara | 545 Nankadawara | 500000 |  | 485000
78 | Developing "Sri Vijitharama Temple " at Mahagama North | 547 Mahagama North | 500000 |  | 483731.67
79 | Developing "Sri Munindarama Temple " at Athuwana | 547 C Athuwana | 500000 |  | 280322.84
80 | Developing "Sri Abiwanarama Temple " at Athuwana |  | 500000 |  | 485000
81 | Developing "Sri Sugatharama Temple " at Mahagama South | 547 A Mahagama North | 500000 |  | 485000
82 | Developing "Sri Sudarshanarama Temple" at Mahabadegama | 537 A Mahabaddegama | 500000 |  | 485000
83 | Developing "St . Sebasthiyan church " at Pattiyagama | 535 Pattiyagama | 500000 |  | 470330.53
84 | Developing "Sri Jayathilinaramaya Temple " at Ihalagama | 536 Ihalagama | 500000 |  | 485000
85 | Developing "Sri Subodharamaya Temple " at Galahitiyawa | 534 C Galahitiyawa | 500000 |  | 484974.5
86 | Developing "Sri Dramarama Temple " at Uraliyagara | 533 Uraliyagara | 500000 |  | 483102.12
87 | Developing "Thinipitiya wiharaya " at Mellawagara | 533 A Mellawagara | 500000 |  | 485000
88 | Developing "Sri Dharmarakkitara'' Temple at Mugunuwatawana | 541 Mugunuwatawana | 500000 |  | 485000
89 | Developing "Sri Ghanodayarama Temple " at Puukkulama | 540 A Puukkulama | 500000 |  | 485000
90 | Developing "Sri Siriwardanarama Temple" at Nelumpokuma | 540 Nelumpokuna | 500000 |  | 485000
91 | Developing "Siri sumana Kusumarama Temple " at Nelumpokuna |  | 500000 |  | 485000
92 | Developing "Sri Pushparama Temple " at Henapola | 542 Henapola | 500000 |  | 477718.87
93 | Developing "Sri Bodirajarama Temple " at Hareendragama | 554 A Hareendragama | 500000 |  | 485000
94 | Developing "Sri Somananndaramaya Temple " at Sembukattiya | 553 Sembukattiya | 500000 |  | 485000
95 | Developing "Siri Sumitharama Temple " at Walaheena | 556 A Walaheena | 500000 |  | 485000
96 | Developing "Madagama church " at Madagama | Madagama | 500000 |  | 485000
97 | Developing "Siri Manikbodi Temple " at Rathmallagara | Rathmallagara | 500000 |  | 485000
98 | Developing "Mugunuwatawana church " at Mugunuwatawana | Mugunuwatawana | 500000 |  | 485000
99 | Developing "Pambala church " at Pambala | Pambala | 500000 |  | 476802.24
100 | Developing "Hareendragama church " at Hareendragama | Hareendragama | 500000 |  | 485000
101 | Developing "Galmuruwa church " at Galmuruwa | Galmuruwa North | 500000 |  | 485000
102 | Developing "Rathnagiriya church " at Rathnagiriya | Rathmallagara | 500000 |  | 484640.84
103 | Developing " Dematapitiya church " at Dematapitiya | Dematapitiya | 500000 |  | 485000
104 | Developing "Koongasyaya Temple " | Koongasyaya | 500000 |  | 463036.98
105 | Developing church at Athwana | 547 C Athuwana | 500000 |  | 485000
106 | Developing church at Potuwila | Potuwila | 500000 |  | 479000
107 | Developing church at Sembukattiya | Sembukattiya | 500000 |  | 485000
109 | Developing "Sri Sugatharama Temple " at Mahagama South | Uthru Mahagama | 400000 |  | 382010.16
111 | Supplying Electricity for Mrs.Thamara Kumari Darmasiri | Mahagama | 20000 |  | 18915.16
113 | Supplying Electricity for Mr.J.A.Ishan Madusanka | Galmuruwa south | 20000 |  | 18915.16
114 | Supplying Electricity for Mr.Wasantha Rathnasiri |  | 20000 |  | 18915.16
115 | Supplying Electricity for Mr.Nalin Indika |  | 20000 |  | 19400
120 | Supplying Electricity for Mr.A.A.Chanaka Sadun Kumara |  | 20000 |  | 18915.16
124 | Supplying Electricity for Mr.I.M.G.Siyantha Disanayaka | Mugunuwatawana | 20000 |  | 19400
127 | Supplying Electricity for Mr.S.G.Sisira Shantha | kachchakaduwa | 20000 |  | 18995.16
130 | Supplying Electricity for Mrs.Ani Merry rotilda | Athwana | 20000 |  | 18915.16
132 | Supplying Electricity for Mrs.W.A.Premawathi | kachchakaduwa | 20000 |  | 18915.16
133 | Supplying Electricity for Mr.H.V.Pradeep Madusanka | Rathnagiriya | 20000 |  | 18915.16
134 | Supplying Electricity for Mr.W.S.Juud Fransis | Panirendawa | 20000 |  | 18915.16
135 | Supplying Electricity for Mrs.R.R.M.Vindhaya Wilasani | Kudabingiriya | 20000 |  | 18915.16
137 | Repairring the pitawana at Koongasyaya Tank | Koongasyaya | 500000 |  | 484456.52
139 | Developing "Mr.S.A.Ranjith Pramalal"s Home at Manakkulama | Manakkulama | 100000 |  | 97000
140 | Developing "Mr.H.M.Kusumalatha's Home at Manakkulama |  | 100000 |  | 51455
141 | Developing "Mrs.N.Ruupika Dilhani 's Home at Manakkulama |  | 100000 |  | 97000
142 | Developing "Mr.W.Nalin Susantha's at Manakkulama |  | 100000 |  | 97000
143 | Developing "Mr.M.A samantha's at Manakkulama |  | 100000 |  | 97000
144 | Developing "Mr.Sunil Shantha's Home at Manakkulama |  | 100000 | 100000 | 97000
145 | Dematapitiya Developing "Mr.J.A.P.Perera 's Home at Dematapitiya | Dematapitiya | 100000 |  | 97000
146 | Developing "Mrs.H.A.M.Jayani Prasansa 's Home at Idigaswila | Idigaswila | 100000 |  | 97000
147 | Developing "Mr.W.Jems Shelton Milroi's Home at Idigaswila |  | 100000 |  | 81124.4
148 | Developing "Mr.W.P.Sisira 's Home at Mahagama | Mahagama South | 100000 |  | 97000
149 | Developing "Mr.R.P.Ranjani 's Home at Mahagama |  | 100000 |  | 97000
151 | Developing "Mr.R.P.Lani Dammika 's Home at Mahagama |  | 100000 |  | 97000
152 | Developing "Mr.Mikal Thamel 's Home at Pambala | Pambala | 100000 |  | 77925
153 | Developing "Mr.T.A.Ashan Maduranga fernando's Home at Athwana | Athwana | 100000 |  | 95631.96
154 | Developing "Mr.K.A.D.Sandeepa Pradeep's Home at Athwana |  | 100000 |  | 97000
155 | Developing "Mr.Salinda Udayanga Kuruwita 's Home at Athwana |  | 100000 |  | 97000
156 | Developing "Mr.M.P.D.Wiraj Kusumsiri 's Home at Athwana |  | 100000 |  | 97000
157 | Developing "Mr. K.A. Uditha Kumarasinghe's Home at Thambagalla Batahirawaththa | Thambagalla Batahira | 100000 |  | 97000
158 | Developing "Mr. H. Jayathilaka's Home at Rathmalagara | Rathmalagara | 100000 |  | 97000
159 | Developing "Mrs. W. Jenat Sriyani's Home at Rathnagiriya | Rathnagiriya | 100000 |  | 97000
160 | Developing "Mr. Besil Dayas's Home at Rathnagiriya |  | 100000 |  | 97000
161 | Developing "Mrs. W. Wijesekara Home at Rathnagiriya |  | 100000 |  | 97000
163 | Developing "Mrs. C.W. Sadhaya kumari's Home at Kuda Bingiriya | Kudabingiriya | 100000 |  | 97000
164 | Developing "Mrs. R.M. Geetha Randeni's Home at Kuda Bingiriya |  | 100000 |  | 97000
166 | Developing "Mr. W.S. Jud Fransis's Home at Panirendawa | Panirendawa | 100000 |  | 97000
167 | Developing "Mrs. W.S. Seetha's Home at Panirendawa |  | 100000 |  | 97000
168 | Developing "Mr. D.A. Nimal Hemantha's Home at Panirendawa |  | 100000 |  | 97000
169 | Developing "Mr. W.P. Inoka Damayanthi's Home at Panirendawa |  | 100000 |  | 97000
170 | Developing "Mr. S.P. Shantha Nandasiri's Home at Sembukattiya | Sembukattiya | 100000 |  | 97000
171 | Developing "Mr. S.D. Duminda Tharanga's Home at Sembukattiya |  | 100000 |  | 97000
172 | Developing "Mr. G.L.P. Upul Chanaka's Home at Sembukattiya |  | 100000 |  | 97000
173 | Developing "Mr. S.Asok lumara Home at Karukkuwa | karukkuwa | 100000 |  | 97000
174 | Developing "Mr. S.P. piyaedasa's Home at Karukkuwa |  | 100000 |  | 97000
175 | Developing "Mr. N. Priyankara Silwa's Home at Karukkuwa |  | 100000 |  | 75923.02
176 | Developing "Mr. I.M.Kasun Diludha's Home at Pambala Dakuna | Koongasyaya | 100000 |  | 84086.78
177 | Developing "Mr. E.M.N. Rathnasiri's Home at Pothuwila | Pothuwila | 100000 |  | 97000
178 | Developing "Mr. N.A. Pradeep Milan Perera's Home at Pothuwila |  | 100000 |  | 97000
179 | Developing "Mr. S.P. Duminda Iresh Kumara's Home at Pothuwila |  | 100000 |  | 97000
180 | Developing "Mrs. E.M. Malani Swarnalatha's Home at Kachchakaduwa | Kachchakaduwa | 100000 |  | 82862.5
182 | Developing "Mrs. K. Piyaseeli's Home at Karukkuwatawana | Karukkuwatawana | 300000 |  | 291000
183 | Developing "Mr. W.G.D. Nishantha Dayananda's Home at Uraliyagara | Uraliyagara | 100000 |  | 97000
184 | Developing "Mrs. W.M. Milani Asankada Silwa's Home at Uraliyagara |  | 100000 |  | 97000
186 | Developing "Mr. W.K. Sarath Priyalal Peris's Home at Mellawagara | Mellawagara | 100000 |  | 97000
187 | Developing "Mr. S.A. Awantha's Home at Mellawagara |  | 100000 |  | 97000
188 | Developing "Mrs. K. Isanka Sadamali's Home at Irattakulama Uthura | Irattakulama Uthura | 100000 |  | 97000
189 | Developing "Mrs. K. Piyumi Nelum Sugandika's Home at Irattakulama Dakuna | Irattakulama Dakuna | 100000 |  | 97000
190 | Developing "Mr. E.A.H.P. Perera's Home at Irattakulama Dakuna |  | 100000 |  | 97000
191 | Developing "Mr. Chamila Indika Nishantha's Home at Galahitiyawa | Galahitiyawa | 100000 |  | 52520
194 | Developing "Mrs. T.K. Nirosha Anuruddika's Home at Pattiyagama | Pattiyagama | 100000 |  | 97000
195 | Developing "Mr. J.A. nilan Kumara's Home at Pattiyagama |  | 100000 |  | 97000
196 | Developing "Mr. M.M.S. Prasanna Perera's Home at Egodayagama | Egodayagama | 100000 |  | 97000
197 | Developing "Mr. M. Somalatha 's Home at Ihalagama | Ihalagama | 100000 |  | 97000
198 | Developing "Mr. H.M.NaZeer's Home at Marakkalagama | Marakkalagama | 100000 |  | 97000
201 | Developing "Mrs. S.P. Nilanthi Reeta Manel's Home at Mugunuwatawana | Mugunuwatawana | 100000 |  | 97000
202 | Developing "Mrs. Sumangala Damayanthi's Home at Galmuruwa Dakuna | Galmuruwa Dakuna | 100000 |  | 97000
203 | Developing "Mrs. S. Suneetha Lakmini's Home at Pallekele | Pallekele | 100000 |  | 97000
204 | Developing "Mr. W.S.D. Dileep Rohan Pranandu's Home at Pallekele |  | 100000 |  | 97000
| Total |  | 96040000 | 100000 | 82119816.53
500000
500000
500000
500000
500000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
1096970.72
1097000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
500000
500000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
2000000
1000000
1500000
1000000
1000000
500000
500000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
1000000
500000
2000000
2000000
2000000
2000000
2000000
2000000
2000000
2000000
1000000
500000
1000000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
500000
300000
400000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
20000
500000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
300000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000
100000